## StitchMind WBS & Task List
StitchMind Enterprise Garments ERP — Work Breakdown Structure (WBS)
Technology Stack: .NET Core 10 ¦ Next.js ¦ MS SQL Server ¦ RabbitMQ ¦ QuestPDF
Task ID | Phase / Module Name | Task Description & Functional Scope | Tech Stack & Implementation Layer | ETA (Days)
Phase 0: Architecture, Docker & Core Foundation (Sprint 1-2)
FND-01 | Foundation | Docker environment setup (mssql, rabbitmq, api, nextjs) | Docker, Docker Compose | 3
FND-02 | Foundation | ASP.NET Core 10 Clean Architecture scaffolding & EF Core base repositories | C#, .NET 10 | 5
FND-03 | Foundation | RabbitMQ Event-Bus configuration (Exchanges, Queues, DLQ, MassTransit) | RabbitMQ, C# | 4
FND-04 | Foundation | Next.js core scaffolding (App Router, Tailwind, Shadcn/UI layout) | Next.js, TypeScript | 4
FND-05 | Foundation | QuestPDF base engine setup & background worker service architecture | C#, QuestPDF | 3
Phase 1: Settings, RBAC Security & Master Data (Sprint 3-5)
SEC-01 | Security | User management, password policies & JWT/MFA authentication | Identity, JWT, NextAuth | 5
SEC-02 | Security | Granular RBAC matrix engine (View, Create, Edit, Delete, Approve, Export) | Custom Claims, Middleware | 6
SEC-03 | Security | Data-level price masking engine for production floor users | DTO Projections, SQL Policy | 4
SEC-04 | Security | Configurable multi-level approval workflow engine | State Machine, Workflow Tables | 7
SEC-05 | Security | Immutable system audit trail (EF Core change interceptor) | EF Core Interceptors, SQL | 4
SEC-06 | Master Data | Master data directory (Buyer, Style, Color, Size, Fabric, Currency) | Next.js CRUD, Web API | 5
SEC-07 | Reports | Reports: Immutable Audit Trail Log & Role-Permission Matrix PDF | QuestPDF Fluent API | 3
Phase 2: Procurement, Thread Production & Merchandising (Sprint 6-10)
PRO-01 | Procurement | Material Requisition (MR) creation linked to Buyer Style IDs | Web API, Next.js UI | 5
PRO-02 | Procurement | Request for Quotation (RFQ) & Comparative Statement (CS) grid | Next.js Dynamic Tables | 5
PRO-03 | Procurement | Pre-budget validation lock (blocks PO exceeding pre-costing) | Business Rule Validator | 4
PRO-04 | Procurement | Purchase Order (PO) creation, approvals & status lifecycle | Workflow Engine, Web API | 6
PRO-05 | Procurement | Commercial import & Back-to-Back (B2B) LC tracking | SQL Ledger, Web API | 6
PRO-06 | Procurement | Goods Receipt Note (GRN) & Quarantine stock intake handling | Stock Events, RabbitMQ | 5
PRO-07 | Procurement | Supplier directory, scoring & performance analytics | Analytical Engine, Dapper | 4
THP-01 | Thread Prod | Raw cotton/yarn inward, spinning, drawing & winding batch logs | Stock Batches, Web API | 6
THP-02 | Thread Prod | Dyeing chemical recipe calculation engine & cost breakdown | C# Recipe Algorithm | 5
THP-03 | Thread Prod | Thread tensile/strength testing & cone barcode packaging | Barcode Gen, Web API | 4
PRO-RPT | Reports | Reports: Commercial PO, PO vs GRN Variance & Thread Lab Certificates | QuestPDF Fluent API | 5
Phase 3: Stock, Warehouse & Cutting Department (Sprint 11-16)
WHS-01 | Warehouse | Bin & Rack 3D coordinate location mapping engine | SQL Tree, Location UI | 5
WHS-02 | Warehouse | Fabric roll barcode/QR tracking (GSM, Cuttable Width, Shade Group) | Zebra ZPL, Barcode API | 6
WHS-03 | Warehouse | Customs Bond register & Utilization Permit (UP) balance engine | Audit Logic, SQL Store | 7
WHS-04 | Warehouse | Store Issue Note (SIN) & Remnant/Cut-piece inventory management | Issue Workflow, Web API | 5
WHS-05 | Warehouse | Physical inventory cycle counting & variance adjustment authorization | Stock Adjustment Engine | 4
CUT-01 | Cutting | CAD marker file ingestion & planned consumption benchmark parser | Marker Ingestion Parser | 6
CUT-02 | Cutting | Knit fabric relaxation time-lock & temperature monitoring engine | Time-lock Validators | 4
CUT-03 | Cutting | Lay planning, spreading logs & stripe/check pattern matching control | Cutting Tables UI | 5
CUT-04 | Cutting | Automated bundle ticket & barcode generation engine (Thermal/A4) | SkiaSharp, Barcode Gen | 6
CUT-05 | Cutting | Cut panel numbering, sorting & fusing machine parameter logging | Part Tracker, Web API | 4
CUT-06 | Cutting | Subcontract cutting delivery & return shortage reconciliation | Subcontract Ledgers | 5
WHS-RPT | Reports | Reports: FIFO Stock Ledger, Bond UP Audit & Planned vs Actual Wastage | QuestPDF Fluent API | 6
Phase 4: Sewing Floor, IoT/Tablet QC & Line Balancing (Sprint 17-22)
IE-01 | Sewing/IE | IE operation bulletin, step breakdown & SMV/SAM allocation | IE Master UI, Web API | 6
SEW-01 | Sewing Floor | Pitch diagram & real-time line balancing calculation assistant | Calculation Engine | 5
SEW-02 | Sewing Floor | Sub-second bundle barcode scanning API for floor stations | Dapper, Fast Scanning API | 7
SEW-03 | Sewing Floor | Real-time floor WIP tracking & bottleneck detection algorithm | RabbitMQ, Redis/Memory | 6
SEW-04 | Sewing Floor | Digital Andon board WebSocket data feed for overhead line displays | WebSockets, SignalR, UI | 5
SEW-05 | Maintenance | Sewing machine allocation, breakdown tickets & MTTR/MTBF analytics | Asset Maintenance Log | 5
SEW-06 | Compliance | Broken needle exchange compliance policy & fragment verification log | Compliance Workflow | 3
QC-01 | Quality Control | Raw fabric 4-Point System inspection engine (Auto Pass/Fail) | 4-Point Math Calculator | 5
QC-02 | Quality Control | Tablet-friendly In-Line Traffic Light QC audit interface | Touch-first UI, Fast POST | 5
QC-03 | Quality Control | Visual garment defect heatmap & End-of-Line rejection log | SVG/Canvas Heatmap | 6
QC-04 | Quality Control | Final pre-shipment AQL sampling engine (ISO 2859-1) & CAPA workflow | Audit Standard Engine | 5
SEW-RPT | Reports | Reports: Hourly Production (HPM), Line Efficiency, Pareto Defect & AQL Cert | QuestPDF Fluent API | 6
Phase 5: Finished Goods & Ex-Factory Shipment (Sprint 23-25)
SHP-01 | Shipment | Carton packing list generator with gross weight check validation | Carton Packing Engine | 5
SHP-02 | Shipment | Finished Goods (FG) inventory warehouse management | Finished Stock Ledger | 4
SHP-03 | Shipment | Container/truck barcode loading audit & dispatch verification | Barcode Verification | 4
SHP-04 | Shipment | Commercial Ex-Factory gate pass execution & order 'Shipped' status lock | Status Workflow, Lock API | 5
SHP-RPT | Reports | Reports: Official Ex-Factory Gate Pass, Packing List & Dispatch Dossier | QuestPDF Fluent API | 4
Phase 6: Accounting, Finance & Commercial Trade (Sprint 26-30)
ACC-01 | Finance | Multi-layer Chart of Accounts (COA) & automated double-entry vouchers | Double-entry Accounting | 7
ACC-02 | Finance | Automated Three-Way Matching (PO + GRN + Vendor Bill verification) | Reconciliation Engine | 7
ACC-03 | Finance | Export Master LC, B2B LC settlements & bill discounting (FDBP) ledger | Commercial Trade Module | 8
ACC-04 | Finance | Order-wise pre-costing vs actual post-costing margin variance engine | Cost Accounting Logic | 7
ACC-05 | Finance | Multi-currency engine (USD/EUR/GBP) with automated Forex gain/loss | FX Conversion Tables | 4
ACC-06 | Finance | Fixed asset depreciation engine & withholding tax/VAT (TDS/VDS) deductions | Automated Ledger Rules | 5
ACC-07 | Finance | Accounts Payable/Receivable aging analysis & payment disbursement run | Financial Scheduling | 5
ACC-RPT | Reports | Reports: Balance Sheet, P&L, Cash Flow, Trial Balance & Order Profitability | QuestPDF Fluent API | 7
Phase 7: HR, Compliance & Dual-Stream Payroll (Sprint 31-34)
HR-01 | HR | Digital service book & child labor age validation screening (<18 yrs block) | Validation, Doc Store | 5
HR-02 | HR | Biometric device (ZKTeco/Facial) real-time TCP/IP synchronization listener | TCP/IP Socket Listener | 7
HR-03 | HR | Dynamic shift rotation, roster scheduling & late deduction penalty engine | Shift Engine, Scheduler | 5
HR-04 | Compliance | Earned leave encashment & statutory maternity benefits calculator | Compliance Benefit Math | 5
HR-05 | Payroll | Dual-stream payroll (Monthly Staff salary + Floor piece-rate + OT/EOT) | Batch Payroll Engine | 8
HR-06 | Payroll | Automated bank & Mobile Financial Services (bKash/Nagad) payout file exporter | Formatted File Exporter | 4
HR-07 | Compliance | Occupational health clinic logs, worker grievance box & disciplinary actions | HR Incident Management | 4
HR-RPT | Reports | Reports: Master Salary Sheet, OT Compliance Audit, Bilingual Pay Slips | QuestPDF Fluent API | 6
Phase 8: Background Scheduler & Automated Email System (Sprint 35)
SCH-01 | Automation | Quartz.NET cron-trigger manager & database execution schedule tables | Quartz.NET, C# Worker | 4
SCH-02 | Automation | In-memory QuestPDF rendering pipeline optimization (MemoryStream buffers) | C# Memory Profiling | 3
SCH-03 | Automation | Secure SMTP / SES email dispatcher service with automated retry policies | MailKit, Error Handlers | 3
SCH-04 | Automation | End-to-End scheduled email test (8:00 PM automated management digest delivery) | Integration Testing | 3
Phase 9: System Integration, Stress Testing & Go-Live (Sprint 36)
UAT-01 | Testing | End-to-End cross-module lifecycle testing (MR -> PO -> Cut -> Sew -> Ship -> Pay) | Full Team QA | 5
UAT-02 | Testing | 2,000+ concurrent floor barcode scans & tablet stress testing | k6 / JMeter Stress Test | 4
UAT-03 | DevOps | Production Docker deployment setup, reverse proxy & automated DB backups | CI/CD, Production Nginx | 4
TOTAL ESTIMATED EFFORT (DEVELOPMENT & QA)